SECTION 01310

CONSTRUCTION SCHEDULES

  - GENERAL

    - Within 30 days after EFFECTIVE DATE OF AGREEMENT, the Contractor shall prepare and submit to the Engineer estimated construction progress schedules for the Work

    - Submit revised progress schedules periodically

    - Additional Requirements Specified Elsewhere

      - Section 01010:  Summary of Work

      - Section 01025:  Measurement and Payment

      - Section 01200:  Project Meetings

      - Section 01340:  Shop Drawings, Product Data, and Samples

  - FORM OF SCHEDULES

    - Prepare schedules in the form of a horizontal bar chart

      - Provide separate horizontal bar for each trade or occupation

      - Horizontal time scale:  Identify the first work day of each week

      - Maximum sheet size:  24"x36"

  - CONTENT OF SCHEDULES

    - Construction progress schedules to include

      - The complete sequence of construction by activity

      - The dates for the beginning and completion of each major element in each major area of construction

  - SUBMISSIONS

    - Submit initial schedules in accordance with paragraph 1.1 of this section

      - Engineer will review schedules and return review copy within 10 days after receipt

      - If required, resubmit within 7 days after return of review copy

    - Submit revised progress schedules as necessary but no less frequently than once per 30 calendar days

      - Provide detailed work activity schedules weekly showing planned activities for three-weeks in advance

    - Contractor shall submit progress schedules as specified by Engineer on Owner's internet based FTP site

      - Contractor shall furnish paper copies of 3-week schedule at each construction progress meeting in addition to posting on the Owner's internet based FTP site no less than twelve (12) hours prior to start of meeting

  - DISTRIBUTION

    - As specified by Owner and Engineer by posting or filing on the Owner’s internet based FTP site

    - Schedule recipients will report promptly to Engineer and Contractor, in writing, any problems anticipated by the projections shown on the schedules

END OF SECTION