SECTION 01340

SHOP DRAWINGS, PRODUCT DATA, AND SAMPLES

  - GENERAL

    - Contractor shall submit shop drawings, product data and samples as required by the Contract Documents for all materials and equipment to be furnished under this Contract

    - Related Requirements Specified Elsewhere

      - Definitions and additional responsibilities of parties:  General Conditions and Supplemental General Conditions

    - Additional Requirements Specified Elsewhere

      - Section 01310:  Construction Schedules

      - Section 01400:  Quality Control

      - Section 01700:  Contract Closeout

      - Section 01730:  Operating and Maintenance Data

    - Designate in the construction schedule, or in a separate coordinated shop drawing schedule, the dates for submission and the dates that reviewed shop drawings and product data will be needed

    - Contractor shall coordinate with and participate in electronic data transfer, filing, storage, retrieval and maintenance of Owner's project "FTP" site as specified by the Owner and Engineer

  - SHOP DRAWINGS

    - Drawings shall be presented in a clear and thorough manner

      - Details shall be identified by reference to sheet and detail, schedule or room numbers shown on the Contract Drawings

      - Drawings shall have sufficient detail to show the kind, size, arrangement and function of component materials and devices

    - Minimum sheet size:  8½"x11"

  - PRODUCT DATA

    - Preparation

      - Clearly mark each copy to identify pertinent products or models

      - Show performance characteristics and capacities

      - Show dimensions and clearances required

      - Show wiring or piping diagrams and controls

      - Show external connections, anchorages and supports required

    - Manufacturer's standard schematic drawings and diagrams

      - Modify drawings and diagrams to delete information which is not applicable to the Work

      - Supplement standard information to provide information specifically applicable to the Work

      - Plot performance points specified

  - SAMPLES

    - Office samples shall be of sufficient size and quantity to clearly illustrate

      - Functional characteristics of the product, with integrally related parts and attachment devices

      - Full range of color, texture and pattern

  - CONTRACTOR RESPONSIBILITIES

    - Contractor shall review shop drawings and product data prior to submission

    - Contractor shall determine and verify

      - Field measurements

      - Field construction criteria

      - Catalog numbers and similar data

      - Conformance with Specifications

    - Contractor shall coordinate each submittal with requirements of the Work and the Contract Documents

    - Contractor shall notify the Engineer in writing, at the time of submission, of any deviations in the submittals from requirements of the Contract Documents

    - Contractor shall certify Contractor's review and conformity to Contract requirements per General Conditions

  - SUBMISSION REQUIREMENTS

    - Initial and secondary submittals shall be made with electronic files and an electronic letter of transmittal to the Engineer by the Contractor and not by subcontractors, suppliers or manufacturers

      - Final submittals of accepted documents shall be made with a complete set of electronic files, paper copies in the quantities indicated below, and a paper letter of transmittal from the Contractor to the Engineer

    - Make submittals promptly in accordance with construction schedule and in such sequence as to cause no delay in the Work or in the work of any other contractor

    - Number of submittals required

      - Initial and secondary submittals shall be made with one set of electronic files to Owner's FTP site

        - Provide in Portable Document Format (.pdf) and AutoDesk AutoCAD Drawing Version 2004 or newer as appropriate to the submittal material

      - Shop drawings and product data

        - Following final acceptance, submit the number of copies which Contractor requires plus three copies which will be distributed by Engineer

      - Product data

        - Following final acceptance, submit the number of copies which Contractor requires plus three copies which will be distributed by Engineer

        - Do not submit less than five copies

      - Samples:  Submit three copies of each office sample unless otherwise directed and/or agreed

    - Submittals shall contain

      - The date of submission and the dates of any previous submissions

      - The project title and number

      - Contract identification where applicable

      - The names of

        - Contractor

        - Supplier

        - Manufacturer

      - Identification of the product, with the specification section number

      - Field dimensions, clearly identified as such

      - Relation to adjacent or critical features of the Work or materials

      - Applicable standards such as ASTM or Federal Specification numbers

      - Identification of deviations from Contract Documents

      - Identification of revisions on resubmittals

      - An 8"x3" blank space for Contractor's and Engineer's stamps

      - Contractor's stamp, signed, certifying to review of submittal, verification of products, field measurements and field construction criteria, and coordination of the information within the submittal with requirements of the Work and Contract Documents

    - Enumeration of Submittals and Resubmittals

      - Combine all information on materials and equipment which are components of a system into one submittal

      - Number each submittal sequentially with applicable specification section:  11306-01, 11306-02, 11306-03, etc.

      - Groups of submittals transmitted under one submittal number will not be accepted unless all submittals are for components of an individual system

      - Resubmittals shall bear the number of the original submittal followed by a letter (A, B, etc.) indicating the order of the resubmittal:  11306.01A, 11306-01B, etc.

  - DISPOSITION OF SHOP DRAWINGS AND PRODUCT DATA

    - No Exception Taken

      - One copy sent to Owner

      - One copy sent to resident project representative

      - One copy retained in Engineer's files

      - Remaining copies returned to Contractor for his use

        - A minimum of one copy to be kept on file at Contractor's field office

        - Remaining copies for Contractor's office file, suppliers or subcontractors

      - Copy of transmittal letter to Owner

    - Make Corrections Noted, Do Not Resubmit

      - One copy sent to Owner

      - One copy sent to resident project representative

      - One copy retained in Engineer's files

      - Remaining copies returned to Contractor for his use

        - One copy to be kept on file at Contractor's field office

        - Remaining copies for Contractor's office file, suppliers or subcontractors

      - Contractor shall assure that Work performed or products furnished comply with exceptions noted on submittal

      - Copies of submittal data in operating and maintenance manuals shall be revised by Contractor according to exceptions

      - Copy of transmittal letter to Owner

    - Revise and Resubmit, Resubmittal Required

      - One copy sent to resident project representative at Engineer's discretion

      - One copy retained in Engineer's files

      - Marked, annotated or edited electronic file will be returned to Contractor for revision and resubmittal

        - Engineer and/or Owner may respond with separate documents describing exceptions taken and revisions and/or additional submittal content required

      - Remaining unmarked copies returned to Contractor

      - Copy of transmittal letter to Owner

  - DISPOSITION OF SAMPLES

    - No Exceptions Noted

      - One sample to Owner

      - One sample to resident project representative

      - One sample retained in Engineer's file

      - Acknowledgment to Contractor

      - Copy of transmittal letter to Owner

    - Make Corrections Noted, Do Not Resubmit

      - One sample to Owner

      - One sample to resident project representative

      - One sample retained in Engineer's file

      - Acknowledgment to Contractor:  Work performed or products furnished to comply with exceptions noted in acknowledgment

      - Copy of transmittal letter to Owner

    - Revise and Resubmit, Resubmittal Required

      - One sample to resident project representative

      - One sample retained in Engineer's file

      - One sample to Contractor for revision and resubmittal

      - Copy of transmittal letter to Owner

  - RESUBMISSION REQUIREMENTS

    - Contractor shall thoroughly review Engineer's comments and make any corrections or changes in the submittals required by Engineer and resubmit until accepted

    - The Engineer may, at his discretion, require the Contractor to reimburse the Owner for costs associated with review of shop drawings and/or product data which require more than one resubmittal

      - Engineer's decision shall be based on thoroughness of submittals

      - Costs not to exceed $500 per submittal

      - Contractor shall execute a Change Order to the Contract deducting the cost paid by the Owner for review of more than one resubmittal of shop drawings and/or product data

      - Refer to Section 01700 - Contract Closeout for additional requirements

    - Shop Drawings and Product Data

      - Contractor shall revise initial drawings or data and resubmit as specified for the initial submittal

      - Contractor shall indicate any changes which have been made other than those requested by Engineer

    - Samples:  Contractor shall submit new samples as required for initial submittal

  - ENGINEER'S RESPONSIBILITIES

    - Review submittals with reasonable promptness and in accordance with schedule

      - No extensions of time are allowed due to Engineer's delay in reviewing submittals unless all the following criteria are met

        - Contractor has notified Engineer in writing that timely review of the particular submittal in question is critical to the progress of the Work

        - Engineer has failed to return submittal within 21 days of receipt of the submittal or said notice, whichever is later

        - Contractor demonstrates that the delay in the progress of the Work was directly attributable to Engineer's failure to return the submittal within 21 days

        - Acceptable schedule of submittals submitted per Section 01310

      - No extensions of time are allowed due to delays in the progress of the Work caused by rejection and subsequent resubmission of data, including multiple resubmissions

    - Review drawings and data submitted only for general conformity with the Contract Documents

      - Engineer's review of drawings and data returned marked "No Exception Taken" or "Exceptions Noted" does not indicate a thorough review of all dimensions, quantities, and details of the material, equipment, device or items shown

      - Engineer's review does not relieve Contractor of responsibility for errors, omissions, deviations or responsibility for compliance with the Contract Documents

    - Consider and review only those deviations from the Contract Documents clearly identified as such in the submittals

    - Affix stamp and indicate requirements for resubmittal or acceptance of submittal

    - Return submittals to Contractor for distribution or for modifications and resubmissions

    - Transmit, unreviewed, to Contractor all copies of submittals received directly from suppliers, manufacturers and subcontractors or submitted without Contractor's certification of review

  - OWNER'S RESPONSIBILITIES

    - Thoroughly review all shop drawings, product data, transmittal letters, etc. forwarded to Owner by Engineer

    - Promptly notify Engineer of any exceptions, comments or questions

END OF SECTION